## Sheet 1 Backend Milestones Over
Milestone ID | Milestone Name | Goal | Owner | Status | Start Date | End Date
M1 | Backend Foundation | System boundaries & setup | Backend
M2 | Data Models | Raw vs processed separation | Backend
M3 | Job Orchestration | Async lifecycle via MQ | Backend
M4 | Scraping Worker | Real data acquisition | Backend
M5 | Normalization & Dedup | Clean structured data | Backend
M6 | AI Filtering | Scoring & intent classification | Backend
M7 | Subscription Enforcement | Monetization logic | Backend
M8 | Export & Delivery | Data consumption | Backend
M9 | Compliance & Provenance | Traceability & trust | Backend
M10 | Demo Hardening | Stability & polish | Backend

## Sheet 2 Milestone 1 – Backend F
Milestone 1 – Backend Foundation
Task ID | Description | Component | Dependency | Status
M1-T1 | Initialize Python project (3.11+) | Core | None | Done
M1-T2 | Configure PostgreSQL connection | Core | M1-T1 | Done
M1-T3 | Configure RabbitMQ connection | Core | M1-T1 | Done
M1-T4 | Environment config (dev/prod) | Core | M1-T1 | Done
M1-T5 | Centralized logging | Core | M1-T1 | Done
M1-T6 | Global error handling | Core | M1-T1 | Done
Milestone 2 – Data Models
Task ID | Description | Table / Module | Status
M2-T1 | Define Job schema | jobs
M2-T2 | Define RawScrapedData schema | raw_scraped_data
M2-T3 | Define ProcessedLead schema | processed_leads
M2-T4 | Enforce raw immutability | raw_scraped_data
M2-T5 | Implement migrations | DB
M2-T6 | Add indexes (job_id, canonical_id) | DB
Milestone 3 – Job Lifecycle & MQ
Task ID | Description | Component | Status
M3-T1 | Job creation API | API
M3-T2 | Publish job to RabbitMQ | API
M3-T3 | Implement job states | Core
M3-T4 | Retry logic with limits | Worker
M3-T5 | Dead-letter queue | MQ
M3-T6 | Persist failure reasons | DB
Milestone 4 – Scraping Worker
Task ID | Description | Component | Status
M4-T1 | Worker service setup | Worker
M4-T2 | Consume jobs from MQ | Worker
M4-T3 | Implement scraper (1 source) | Scraper
M4-T4 | Rate limiting | Scraper
M4-T5 | Timeout & retry handling | Scraper
M4-T6 | Persist raw scraped data | DB
Milestone 5 – Normalization & Deduplication
Task ID | Description | Component | Status
M5-T1 | Text cleanup & parsing | Processor
M5-T2 | Field normalization | Processor
M5-T3 | Canonical identity generation | Processor
M5-T4 | Duplicate grouping | Processor
M5-T5 | Link raw → processed | DB
Milestone 6 – AI Filtering & Scoring
Task ID | Description | Component | Status
M6-T1 | Define AI input contract | AI
M6-T2 | Rule-based baseline scoring | AI
M6-T3 | AI intent classification | AI
M6-T4 | Confidence scoring | AI
M6-T5 | Low-confidence filtering | AI
M6-T6 | Persist scored leads | DB
Milestone 7 – Subscription Enforcement
Task ID | Description | Enforcement Point | Status
M7-T1 | Define plan limits | Core
M7-T2 | Enforce at job creation | API
M7-T3 | Enforce at execution | Worker
M7-T4 | Enforce result visibility | API
M7-T5 | Log enforcement events | Core
Milestone 8 – Export & Delivery
Task ID | Description | Component | Status
M8-T1 | CSV export endpoint | API
M8-T2 | Export permission checks | API
M8-T3 | Export processed leads only | API
M8-T4 | Track export usage | Core
Milestone 9 – Compliance & Provenance
Task ID | Description | Component | Status
M9-T1 | robots.txt awareness flag | Scraper
M9-T2 | Store source attribution | DB
M9-T3 | Persist freshness metadata | DB
M9-T4 | Expose provenance via API | API